## Executive_Summary
CareerConnect Job Portal - Master Project Report
PROJECT LEADS |  | ARCHITECTURE |  | API ENDPOINTS | DATABASE TABLES
Liqae & Shahryar |  | FastAPI + JS |  | 35 Specs | 14 Tables
1. Project Identification & Team Credits
Attribute | Specification & Details
System Name | CareerConnect University Job Portal
Project Leads & Key Engineers | Liqae (Lead Systems Architect & Backend Engineer) Shahryar (Principal Full-Stack Engineer & Database Designer)
Organization | University of Engineering & Technology (UET)
Development Stack | Backend: FastAPI (Python 3.14), Pydantic v2, SQLAlchemy 2.0 ORM, PyMySQL, JWT Auth Frontend: Vanilla HTML5, Custom CSS, Modular JavaScript, Component UI Database: MySQL / MariaDB (Database Name: job_portal)
Target Users & Roles | 1. Students (Profile Builder, Resume Upload, Job Applications, Interview Tracking) 2. Companies (Corporate Verification SECP/NTN/SAP, Job Posting, Candidate Search, Shortlisting) 3. Administrators (Company Verification, Job Moderation, Portal Oversight) 4. Super Administrators (Admin User Management, System Analytics, Global Controls)
Verification Standards | Corporate SECP Registration Number, SAP Corporate ID, National Tax Number (NTN), Verification Document Uploads (PDF/PNG/JPG)
2. Seeded System Accounts
Role Title | Assigned Lead / Owner | Email Address | Default Password | Access Level & Scope
Super Administrator | Liqae & Shahryar | superadmin@jobportal.com | admin123 | Full system privileges, admin user management, platform audit logs
Administrator | Liqae & Shahryar | admin@uetjobportal.com | admin123 | Company approval/rejection workflows, document verification, portal moderation

## Team_&_Resource_Allocation
Project Team Ownership & Module Allocation Matrix
Module / Feature Area | Primary Assigned Lead | Co-Engineer / Reviewer | Key Responsibilities | Deliverables Produced | Verification Status
Backend Architecture & REST Core | Liqae | Shahryar | FastAPI setup, Uvicorn server, Pydantic schemas, dependency injection middleware | backend/app/main.py, config.py, deps.py | Completed
Database Schema & Migration Engine | Shahryar | Liqae | MySQL schema design, foreign keys, 8 migration scripts, seed data generator | database/schema.sql, migrations/*.sql | Completed
Authentication & Security Module | Liqae | Shahryar | JWT token generation, OAuth2 password flow, password hashing, LMS auth integration | backend/app/api/v1/auth.py, services/auth_service.py | Completed
Student Marketplace & Profiles | Shahryar | Liqae | Student profile CRUD, skill percentages, experience/certification models, resume uploads | backend/app/api/v1/student.py, skills.py | Completed
Company Verification & Corporate Onboarding | Liqae | Shahryar | SECP/NTN/SAP document upload, status workflow (pending -> approved/rejected) | backend/app/api/v1/company.py, files.py | Completed
Job Management & Applicant Tracking | Shahryar | Liqae | Job postings, application submission, shortlisting, candidate search engine | backend/app/api/v1/company.py, student.py | Completed
Interview Scheduling & Notifications | Liqae | Shahryar | Interview request workflow (date slots, accept/decline), notification triggers | backend/app/api/v1/notifications.py, interview models | Completed
Admin & Super Admin Portals | Shahryar | Liqae | Company approval UI, admin account creation, super admin dashboard endpoints | backend/app/api/v1/admin.py, super_admin.py | Completed
Frontend Presentation & Shared JS Engine | Liqae & Shahryar | Liqae & Shahryar | Dynamic HTML dashboards, CSS styles, api.js HTTP client, auth.js router | frontend/*, dashboards/*.html, js/*.js | Completed

## Architecture_&_Design
Multi-Layer System Architecture & Technical Specifications
Layer Level | Layer Name | Technology Stack | Design Patterns & Implementation Details | Lead Architectural Designers
Layer 1 | Presentation Layer | HTML5, Vanilla CSS, Modular JS, Custom Components | Decoupled SPA UI served on port 3000. Shared api.js client intercepts requests and appends JWT Bearer headers from localStorage. | Liqae & Shahryar
Layer 2 | API & Routing Layer | FastAPI (Python 3.14), APIRouter, OAuth2 | Exposes REST endpoints under /api/v1 prefix. Uses dependency injection (deps.py) to enforce role guards for student, company, admin, super_admin. | Liqae
Layer 3 | Service & Business Logic | Auth Service, Resume Service, Verification Engine | Enforces corporate registration validation (SECP/NTN/SAP), handles LMS API session handshakes, executes resume parsing routines. | Liqae & Shahryar
Layer 4 | Data Access & ORM Layer | SQLAlchemy 2.0 ORM, PyMySQL, Pydantic v2 | Translates Python models into relational SQL queries. Pydantic schemas validate request inputs and format strict JSON responses. | Liqae
Layer 5 | Relational Database Layer | MySQL / MariaDB (job_portal) | Stores relational entities with foreign key cascades, unique constraints (roll_no, email, SECP), and index optimizations. | Liqae

## Gantt_&_Project_Phases
Detailed Development Phase Schedule & Deliverables Timeline
Phase Name | Task / Module Description | Assigned Lead | Target Duration | Deliverables & Output Files | Execution Status
Phase 1: Requirements & Planning | Requirement Gathering & SRS Specification | Liqae & Shahryar | 3 Days | SRS Document & Software Planning Sheet | Completed
Phase 1: Requirements & Planning | Architecture & Technology Stack Selection | Liqae | 3 Days | FastAPI + Vanilla JS Architecture Specification | Completed
Phase 1: Requirements & Planning | Relational Database Schema Design | Liqae | 3 Days | schema.sql & 8 Migration Scripts | Completed
Phase 2: Backend Core Development | Database ORM Models & Connections Setup | Shahryar | 5 Days | database.py & app/models/*.py | Completed
Phase 2: Backend Core Development | JWT Authentication & LMS Handshake Integration | Liqae | 3 Days | routers/auth.py & services/auth_service.py | Completed
Phase 2: Backend Core Development | Student Profile & Marketplace APIs | Liqae | 5 Days | routers/student.py & routers/skills.py | Completed
Phase 2: Backend Core Development | Company Onboarding & Verification APIs | Liqae | 4 Days | routers/company.py & routers/files.py | Completed
Phase 2: Backend Core Development | Admin & Super Admin Moderation APIs | Shahryar | 4 Days | routers/admin.py & super_admin.py | Completed
Phase 3: Frontend Application Development | Auth Interfaces (Login, LMS Modal, Company Registration) | Liqae | 4 Days | login.html, register-company.html | Completed
Phase 3: Frontend Application Development | Student Dashboard & Profile Builder UI | Liqae | 6 Days | dashboards/student-dashboard.html & .js | Completed
Phase 3: Frontend Application Development | Company Dashboard & Applicant Tracking UI | Liqae | 6 Days | dashboards/company-dashboard.html & .js | Completed
Phase 3: Frontend Application Development | Admin & Super Admin Dashboards | Liqae | 4 Days | admin-dashboard.html & super-admin-dashboard.html | Completed
Phase 4: Integration & Storage | File Upload Handler & Resume Storage System | Liqae & Shahryar | 3 Days | Upload Service & /uploads Directory | Completed
Phase 4: Integration & Storage | Notification Engine Integration | Liqae | 3 Days | routers/notifications.py & DB Trigger Handler | Completed
Phase 5: Testing & Go-Live | Automated Pytest Suite & Validation Scripts | Shahryar | 3 Days | backend/tests/test_auth.py & test_date_validation.py | Completed
Phase 5: Testing & Go-Live | Production Readiness & Python 3.14 Compatibility | Liqae & Shahryar | 2 Days | requirements.txt, setup.ps1, run scripts | Completed

## Backend_API_Specification
Ultra-Detailed Backend REST API Endpoint Specification Matrix
Sr # | Module Category | Endpoint URL | HTTP Method | Access Rights | Payload / Query Parameters | Response Code & Schema | Lead Developer | Status
1 | Authentication | /api/v1/auth/login | POST | Public | JSON: {username, password} | 200 OK -> {access_token, token_type, role} | Liqae | Completed
2 | Authentication | /api/v1/auth/student/login | POST | Public | JSON: {email, password} | 200 OK -> {access_token, token_type, student_profile} | Liqae | Completed
3 | Authentication | /api/v1/auth/lms-login | POST | Public | JSON: {username, password} | 200 OK -> LMS Token & Student Record | Liqae | Completed
4 | Authentication | /api/v1/auth/company/register | POST | Public | Form Data: Company info + SECP/NTN/SAP files | 201 Created -> Company Registration Record (Pending) | Liqae | Completed
5 | Authentication | /api/v1/auth/me | GET | Authenticated | Header: Authorization Bearer | 200 OK -> Current User Profile Object | Liqae | Completed
6 | Student Profile | /api/v1/students/me | GET | Student | Header: Authorization Bearer | 200 OK -> Full Student Profile + Skills + Experience | Shahryar | Completed
7 | Student Profile | /api/v1/students/me | PUT | Student | JSON: {name, department, gpa, bio, links} | 200 OK -> Updated Student Profile Object | Shahryar | Completed
8 | Student Document | /api/v1/students/me/resume | POST | Student | Multipart Form: resume_file (PDF/DOCX) | 200 OK -> {resume_url, filename} | Shahryar | Completed
9 | Student Document | /api/v1/students/me/resume | DELETE | Student | Header: Authorization Bearer | 200 OK -> {message: Resume deleted} | Shahryar | Completed
10 | Student Avatar | /api/v1/students/me/photo | POST | Student | Multipart Form: photo_file (PNG/JPG) | 200 OK -> {photo_url} | Shahryar | Completed
11 | Student Skills | /api/v1/students/me/skills | GET | Student | Header: Authorization Bearer | 200 OK -> Array of [{skill_name, proficiency_percent}] | Shahryar | Completed
12 | Student Skills | /api/v1/students/me/skills | POST | Student | JSON: {skill_name, proficiency_percent} | 201 Created -> Skill Record | Shahryar | Completed
13 | Student Experience | /api/v1/students/me/experiences | POST | Student | JSON: {company_name, title, start_date, end_date} | 201 Created -> Experience Record | Shahryar | Completed
14 | Student Certs | /api/v1/students/me/certifications | POST | Student | JSON: {name, issuer, issue_date, url} | 201 Created -> Certification Record | Shahryar | Completed
15 | Student Jobs Search | /api/v1/students/jobs | GET | Student | Query: ?search=keyword&type=full_time | 200 OK -> List of Published Job Postings | Shahryar | Completed
16 | Student Jobs Detail | /api/v1/students/jobs/{job_id} | GET | Student | Path: job_id | 200 OK -> Detailed Job Posting Specification | Shahryar | Completed
17 | Student Apply | /api/v1/students/jobs/{job_id}/apply | POST | Student | JSON: {cover_letter, custom_resume_url} | 201 Created -> Application Record (Status: applied) | Shahryar | Completed
18 | Student Applications | /api/v1/students/me/applications | GET | Student | Header: Authorization Bearer | 200 OK -> List of Submitted Applications with status | Shahryar | Completed
19 | Student Withdraw | /api/v1/students/me/applications/{id}/withdraw | POST | Student | Path: application_id | 200 OK -> {status: withdrawn} | Shahryar | Completed
20 | Student Interviews | /api/v1/students/me/interview-requests | GET | Student | Header: Authorization Bearer | 200 OK -> List of Received Interview Slots | Liqae | Completed
21 | Student Interviews | /api/v1/students/me/interview-requests/{id}/accept | POST | Student | Path: request_id | 200 OK -> {status: accepted} | Liqae | Completed
22 | Student Interviews | /api/v1/students/me/interview-requests/{id}/decline | POST | Student | Path: request_id | 200 OK -> {status: declined} | Liqae | Completed
23 | Company Profile | /api/v1/company/profile | GET | Approved Company | Header: Authorization Bearer | 200 OK -> Company Corporate Profile & Verification Data | Liqae | Completed
24 | Company Profile | /api/v1/company/profile | PATCH | Approved Company | JSON: {company_name, website, location, bio} | 200 OK -> Updated Company Profile Object | Liqae | Completed
25 | Company Jobs | /api/v1/company/jobs | POST | Approved Company | JSON: {title, description, min_cgpa, employment_type} | 201 Created -> Job Record | Liqae | Completed
26 | Company Jobs | /api/v1/company/jobs | GET | Approved Company | Header: Authorization Bearer | 200 OK -> List of Jobs posted by company | Liqae | Completed
27 | Company Jobs Status | /api/v1/company/jobs/{job_id}/status | PATCH | Approved Company | JSON: {status: draft¦published¦closed} | 200 OK -> Updated Job Status Object | Liqae | Completed
28 | Company Applicants | /api/v1/company/jobs/{job_id}/applications | GET | Approved Company | Path: job_id | 200 OK -> Applicant List with resumes & GPAs | Liqae | Completed
29 | Company Shortlist | /api/v1/company/applications/{id}/shortlist | POST | Approved Company | Path: application_id | 200 OK -> Application Status: shortlisted | Liqae | Completed
30 | Company Interview | /api/v1/company/applications/{id}/interview-request | POST | Approved Company | JSON: {interview_date, message} | 201 Created -> Interview Request Object | Liqae | Completed
31 | Company Talent Search | /api/v1/company/candidates/search | GET | Approved Company | Query: ?skill=Python&department=CS | 200 OK -> Student Marketplace Talent Profiles | Shahryar | Completed
32 | Admin Companies | /api/v1/admin/companies | GET | Admin / Super Admin | Query: ?status=pending | 200 OK -> Company Verification Requests | Shahryar | Completed
33 | Admin Approve | /api/v1/admin/companies/{id}/approve | POST | Admin / Super Admin | Path: company_id | 200 OK -> Company Status: approved | Shahryar | Completed
34 | Admin Reject | /api/v1/admin/companies/{id}/reject | POST | Admin / Super Admin | JSON: {rejection_reason} | 200 OK -> Company Status: rejected | Shahryar | Completed
35 | Super Admin | /api/v1/super-admin/admins | POST | Super Admin | JSON: {name, email, password} | 201 Created -> New Admin Account | Shahryar | Completed

## Frontend_Interface_Matrix
Frontend Application Interfaces & Shared Component Matrix
Task Id | Interface Title | URL Path / File Name | Resource Script | Target User Role | Interface Responsibilities & Features | Lead Engineer | Status
1 | Public Job Landing Page | /index.html | landing.js | Public Visitor | Hero job search banner, public job cards grid, filter by employment type, auth quick links | Liqae | Completed
2 | Unified Auth Login Page | /login.html | login.js | All Roles | Role-aware login form, JWT session persistence, LMS institutional login modal | Liqae | Completed
3 | Company Onboarding Registration | /register-company.html | register-company.js | Public Company | Multi-step corporate registration, SECP/NTN/SAP number inputs, file dropzone | Liqae | Completed
4 | Student Marketplace Dashboard | dashboards/student-dashboard.html | student-dashboard.js | Student | Profile manager, resume drag & drop, skill percentage sliders, job application history | Shahryar | Completed
5 | Company Recruitment Dashboard | dashboards/company-dashboard.html | company-dashboard.js | Company | Job creation modal, candidate search engine, application review drawer, interview scheduler | Liqae | Completed
6 | Admin Verification Dashboard | dashboards/admin-dashboard.html | admin-dashboard.js | Admin | Pending company approval queue, SECP document viewer modal, user moderation controls | Shahryar | Completed
7 | Super Admin Portal Dashboard | dashboards/super-admin-dashboard.html | super-admin-dashboard.js | Super Admin | Admin user creation form, platform activity metrics, global security configuration | Shahryar | Completed
8 | Shared API Engine | frontend/js/api.js | api.js | Frontend Shared | Central HTTP client with automatic Bearer token injection, error handling, JSON serialization | Liqae | Completed
9 | Session & Auth Guard Utility | frontend/js/auth.js | auth.js | Frontend Shared | Validates JWT expiration, redirects unauthorized users to login, role-based dashboard router | Liqae | Completed

## Database_Schema_Dictionary
Comprehensive Database Schema & Data Dictionary (job_portal)
Sr # | Table Name | Column Name | Data Type | Nullable | Key Type | Foreign Key Target | Default Value | Column Description & Business Rules
1 | users | id | BIGINT | NO | PK | - | AUTO_INCREMENT | Unique 64-bit auto-increment user ID
2 | users | email | VARCHAR(255) | NO | UK | - | - | Unique login email address
3 | users | password_hash | VARCHAR(255) | YES | - | - | NULL | Bcrypt password hash string
4 | users | role | ENUM | NO | - | - | - | Role: super_admin, admin, company, student
5 | users | auth_provider | ENUM | NO | - | - | 'local' | Authentication provider: local or lms
6 | users | status | ENUM | NO | - | - | 'active' | Account status: active, disabled, deleted
7 | companies | id | BIGINT | NO | PK | - | AUTO_INCREMENT | Unique corporate company ID
8 | companies | user_id | BIGINT | NO | FK / UK | users.id | - | 1:1 mapping to parent user account
9 | companies | company_name | VARCHAR(255) | NO | - | - | - | Registered business name
10 | companies | secp_number | VARCHAR(100) | YES | - | - | NULL | SECP Corporate Registration Number
11 | companies | sap_number | VARCHAR(100) | YES | - | - | NULL | SAP System Integration Number
12 | companies | ntn_number | VARCHAR(100) | YES | - | - | NULL | National Tax Number (NTN)
13 | companies | status | ENUM | NO | - | - | 'pending' | Corporate status: pending, approved, rejected, disabled
14 | student_profiles | id | BIGINT | NO | PK | - | AUTO_INCREMENT | Unique student profile ID
15 | student_profiles | user_id | BIGINT | NO | FK / UK | users.id | - | 1:1 mapping to student user account
16 | student_profiles | roll_no | VARCHAR(50) | NO | UK | - | - | University student roll number
17 | student_profiles | department | VARCHAR(100) | NO | - | - | - | Academic department (e.g. CS, EE, ME)
18 | student_profiles | gpa | DECIMAL(3,2) | YES | - | - | NULL | Cumulative GPA out of 4.00
19 | student_profiles | resume_path | VARCHAR(500) | YES | - | - | NULL | Storage file path to uploaded resume
20 | student_profiles | photo_path | VARCHAR(500) | YES | - | - | NULL | Storage file path to avatar image
21 | jobs | id | BIGINT | NO | PK | - | AUTO_INCREMENT | Unique job posting ID
22 | jobs | company_id | BIGINT | NO | FK | companies.id | - | Foreign key linking job to company
23 | jobs | title | VARCHAR(255) | NO | - | - | - | Job vacancy title
24 | jobs | employment_type | ENUM | NO | - | - | 'full_time' | full_time, part_time, internship, contract, remote
25 | jobs | min_cgpa | DECIMAL(4,2) | YES | - | - | NULL | Minimum CGPA required to apply
26 | jobs | status | ENUM | NO | - | - | 'draft' | Job status: draft, published, closed, hidden
27 | applications | id | BIGINT | NO | PK | - | AUTO_INCREMENT | Unique job application record ID
28 | applications | job_id | BIGINT | NO | FK | jobs.id | - | Target job posting link
29 | applications | student_profile_id | BIGINT | NO | FK | student_profiles.id | - | Applicant student profile link
30 | applications | status | ENUM | NO | - | - | 'applied' | applied, shortlisted, interviewed, rejected, withdrawn
31 | interview_requests | id | BIGINT | NO | PK | - | AUTO_INCREMENT | Unique interview request ID
32 | interview_requests | application_id | BIGINT | NO | FK / UK | applications.id | - | 1:1 link to job application
33 | interview_requests | interview_date | DATETIME | YES | - | - | NULL | Scheduled interview slot timestamp
34 | interview_requests | status | ENUM | NO | - | - | 'pending' | pending, accepted, declined, cancelled
35 | notifications | id | BIGINT | NO | PK | - | AUTO_INCREMENT | Unique notification alert ID
36 | notifications | user_id | BIGINT | NO | FK | users.id | - | Recipient user account ID
37 | notifications | message | TEXT | NO | - | - | - | Notification message text content
38 | notifications | is_read | BOOLEAN | NO | INDEX | - | FALSE | Read flag (indexed for fast unread counts)