## Hospital_Reg_backend
| Features | Details | Resource | API Sr. No | Priority | Status | HTTP Method | Api End Point | Access Rights | api link | FrontEnd Resource Name | Category | URL | Documentation
1. Project Planning & Design Phase |  |  |  |  | High | Inprgress
[5 empty] | High | Inprgress |  | http://10.10.35.190:5000/index.html
Task 1.1: Requirement Gathering |  |  |  |  | High | Inprgress
Task 1.2: Project Scope Definition |  |  |  |  | High | Inprgress
Task 1.3: DashBoard Design and Layout |  |  |  |  | High | Done
Subtasks:
pending
pending
pending
Task 1.4: Database Schema Design |  |  |  |  | High | Inprgress
Task 1.5: Tech Stack Finalization |  |  |  |  | High | Done
2. Backend Development Phase (API & Admin Management)
Task 2.1: Authentication and Authorization (JWT, Identity Framework) | [6 empty] | HTTP Method | Endpoint |  |  |  | Description
Task 2.1.1: Authentication (JWT, Identity Framework,OTP) | Registration |  | Danish | 1 | High | Inprgress | POST | /api/auth/register |  |  |  | Register a new user (Admin, Evaluator, Hospital Focal Person, etc.)
| Login |  | Danish | 2 | High | Done | POST | /api/auth/login |  |  |  | Authenticate user and issue access + refresh tokens
| Token refresh |  | Danish | 3 | High | Done | POST | /api/auth/email/confirm |  |  |  | Refresh JWT token when the old token expires
| Email Confirmation |  | Danish | 4 | High | Done | POST | /api/auth/email/resend |  |  |  | Confirm user’s email after clicking verification link
| Resend Email Confirmation |  | Danish | 5 | High | Done | POST | /api/auth/forgot-password |  |  |  | Resend email confirmation link to user
| Forgot Password |  | Danish | 6 | High | Done | POST | /api/auth/reset-password |  |  |  | Send password reset link to user’s email
| Reset Password |  | Danish | 7 | High | Done | POST |  |  |  |  | Reset password using the token sent via email
| Two Factor Authentication management |  | Danish | 8 | High | Done | GET | /api/auth/twofactor/status |  |  |  | Get logged-in user’s basic profile info (from token)
| Get Info |  | Danish | 9 | High | Done | PUT | /api/auth/user /api/auth/twofactor/enable /api/auth/twofactor/disable |  |  |  | Update user’s profile info (name, phone, email)
| Post Info |  | Danish | 10 | High | Done | GET | /api/auth/user |  |  |  | Check if 2FA (Two-Factor Authentication) is enabled
| Get roles |  | Usama | 11 | High | InReview | POST | /api/auth/roles |  |  |  | Enable Two-Factor Authentication for account
| Get User Roles |  | Usama | 12 | High | InReview | POST | /api/auth/user/{userId}/roles |  |  |  | Disable Two-Factor Authentication
| Add Roles | Administrator, Phota Admin, Accountant, HR Manager, Hospitals Manager, Surveyor, hospital_subscriber, hospital_deo | Danish | 13 | High | Done | POST | /api/auth/addroles |  |  |  | Fetch all available system roles (Admin, Evaluator, Hospital, etc.)
| Add User Roles |  | Usama | 14 | High | InReview | POST | /api/auth/user/{userId}/roles/{roleId} |  |  |  | Get all roles assigned to a user
| Get All Roles | Retrieve list of all roles | Usama | 301 | High | InReview | GET | /api/roles/getall
| Get Role By ID | Retrieve a specific role by ID | Usama | 302 | High | InReview | GET | /api/roles/getbyid/{id}
| Create Role | Add a new role | Usama | 303 | High | InReview | POST | /api/roles/create
| Update Role | Update an existing role | Usama | 304 | Medium | InReview | PUT | /api/roles/update/{id}
| Delete Role | Delete a role | Usama | 305 | Medium | InReview | DELETE | /api/roles/delete/{id}
| Get Role By Name | Retrieve role by name | Usama | 306 | Low | InReview | GET | /api/roles/getbyname/{name}
Task2.1.2:Modules | Get All Modules | Retrieve list of all modules | Zain | 307 | High | InReview | GET | /api/modules/getall
| Get Module By ID | Retrieve a specific module by ID | Zain | 308 | High | InReview | GET | /api/modules/getbyid/{id}
| Create Module | Add a new module | Zain | 309 | High | InReview | POST | /api/modules/create
| Update Module | Update an existing module | Zain | 310 | Medium | InReview | PUT | /api/modules/update/{id}
| Delete Module | Delete a module | Zain | 311 | Medium | InReview | DELETE | /api/modules/delete/{id}
| Get Module By Name | Retrieve module by name | Zain | 312 | Low | InReview | GET | /api/modules/getbyname/{name}
Task2.1.3:RoleModulePermission
| Get All RoleModulePermissions | Retrieve list of all role-module-permissions | Zain | 313 | High | InReview | GET | /api/rolemodulepermissions/getall
| Get RoleModulePermission By ID | Retrieve a specific role-module-permission by ID | Zain | 314 | High | InReview | GET | /api/rolemodulepermissions/getbyid/{id}
| Create RoleModulePermission | Add a new role-module-permission | Zain | 315 | High | InReview | POST | /api/rolemodulepermissions/create
| Update RoleModulePermission | Update an existing role-module-permission | Zain | 316 | Medium | InReview | PUT | /api/rolemodulepermissions/update/{id}
| Delete RoleModulePermission | Delete a role-module-permission | Zain | 317 | Medium | InReview | DELETE | /api/rolemodulepermissions/delete/{id}
| Get RoleModulePermission By Role | Retrieve all permissions assigned to a role | Zain | 318 | Low | InReview | GET | /api/rolemodulepermissions/getbyrole/{roleId}
Task 2.3: Configurations |  | Phota Admin
Subtasks:
Task2.3.1:TransplantType | Seeding Of all transplant Type |  |  |  | High | Done
| Get all transplant types |  | usama | 15 |  | InReview | GET | /api/transplant-types | [5 empty] | input/output
| Get specific transplant type by ID |  | usama | 16 |  | InReview | GET | /api/transplant-types/{id}
| Create new transplant type |  | usama | 17 |  | InReview | POST | /api/transplant-types
| Update existing transplant type |  | usama | 18 |  | InReview | PUT | /api/transplant-types/{id}
| Delete or deactivate a transplant type |  | usama | 19 |  | InReview | DELETE | /api/transplant-types/{id}
Task2.3.2:AccreditationChecklist | Seeding Of all AccreditationChecklist |  | Danish |  | High | InReview
| Fetch all accreditation checklist items |  | Usama | 20 |  | InReview | GET | /api/accreditation-checklist
| Fetch specific accreditation checklist item |  | Usama | 21 |  | InReview | GET | /api/accreditation-checklist/{id}
| Add new accreditation checklist item |  | Usama | 22 |  | InReview | POST | /api/accreditation-checklist
| Update accreditation checklist item |  | Usama | 23 |  | InReview | PUT | /api/accreditation-checklist/{id}
| Delete/deactivate accreditation item |  | Usama | 24 |  | InReview | DELETE | /api/accreditation-checklist/{id}
| Submit hospital’s responses |  | Usama | 25 |  | InReview | POST | /api/checklist-responses
| Get checklist results for a specific hospital |  | Usama | 26 |  | InReview | GET | /api/checklist-responses/hospital/{hospitalId}
| Add evaluator comments for a checklist item |  | Usama | 27 |  | InReview | POST | /api/checklist-comments
| Upload document proofs (PHCC license, etc.) |  | Usama | 28 |  | InReview | POST | /api/checklist-attachments
Task 2.3.3:Standard | Seeding Of all Standards |  | Danish |  | High | InReview
| Fetch all standards |  | Zain Bin Imran | 29 |  | InReview | GET | /api/standards
| Fetch specific standard by ID |  | Zain Bin Imran | 30 |  | InReview | GET | /api/standards/{id}
| Add new standard |  | Zain Bin Imran | 31 |  | InReview | POST | /api/standards
| Update a standard |  | Zain Bin Imran | 32 |  | InReview | PUT | /api/standards/{id}
| Delete or deactivate standard |  | Zain Bin Imran | 33 |  | InReview | DELETE | /api/standards/{id}
| Get all standards by transplant type |  | Zain Bin Imran | 34 |  | InReview | GET | /api/standards/transplant/{transplantTypeId}
| Save evaluation results for a standard |  | Zain Bin Imran | 35 |  | InReview | POST | /api/standard-evaluations
| Fetch evaluator comments |  | Zain Bin Imran | 36 |  | InReview | GET | /api/standard-comments/{standardId}
| Upload files related to a specific standard |  | Zain Bin Imran | 37 |  | InReview | POST | /api/standard-attachments
Task 2.3.4:Indicator | Seeding Of all Indicators |  | Danish |  | High | InReview
| Fetch all indicators |  | Zain Bin Imran | 38 |  | InReview | GET | /api/indicators
| Fetch specific indicator |  | Zain Bin Imran | 39 |  | InReview | GET | /api/indicators/{id}
| Add new indicator |  | Zain Bin Imran | 40 |  | InReview | POST | /api/indicators
| Update existing indicator |  | Zain Bin Imran | 41 |  | InReview | PUT | /api/indicators/{id}
| Delete/deactivate indicator |  | Zain Bin Imran | 42 |  | InReview | DELETE | /api/indicators/{id}
| Fetch all indicators for a standard |  | Zain Bin Imran | 43 |  | InReview | GET | /api/indicators/standard/{standardId}
| Save indicator evaluation result |  | Zain Bin Imran | 44 |  | InReview | POST | /api/indicator-evaluations
| Get evaluator remarks |  | Zain Bin Imran | 45 |  | InReview | GET | /api/indicator-comments/{indicatorId}
| Upload supporting evidence documents |  | Zain Bin Imran | 46 |  | InReview | POST | /api/indicator-attachments
Task 2.3.5:IndicatorItem | Seeding Of all IndicatorItem |  | Danish |  | High | InReview
| Get all items |  | Usama | 47 |  | InReview | GET | /api/indicator-items
| Get specific item |  | Usama | 48 |  | InReview | GET | /api/indicator-items/{id}
| Add new indicator item |  | Usama | 49 |  | InReview | POST | /api/indicator-items
| Update indicator item |  | Usama | 50 |  | InReview | PUT | /api/indicator-items/{id}
| Delete or deactivate item |  | Usama | 51 |  | InReview | DELETE | /api/indicator-items/{id}
| Get items belonging to an indicator |  | Usama | 52 |  | InReview | GET | /api/indicator-items/indicator/{indicatorId}
| Get items belonging to an specific category |  | Usama | 53 |  | InReview | GET | /api/indicator-items/indicatorItemcategory/{categoryId}
| Submit hospital’s responses (Yes/No, marks) |  | Usama | 54 |  | InReview | POST | /api/indicator-item-responses
| Get all responses for a hospital |  | Usama | 55 |  | InReview | GET | /api/indicator-item-responses/hospital/{hospitalId}
| Upload supporting file/document |  | Usama | 56 |  | InReview | POST | /api/indicator-item-attachments
| Fetch evaluator’s remarks |  | Usama | 57 |  | InReview | GET | /api/indicator-item-comments/{itemId}
Task 2.3.6:IndicatorItemCategory | Seeding Of all IndicatorItemCategory |  | Danish |  | High | InReview
| Fetch all categories |  | Zain Bin Imran | 58 | High | InReview | GET | /api/indicator-item-categories
| Fetch a specific category |  | Zain Bin Imran | 59 | High | InReview | GET | /api/indicator-item-categories/{id}
| Add a new category |  | Zain Bin Imran | 60 | High | InReview | POST | /api/indicator-item-categories
| Update a category |  | Zain Bin Imran | 61 | High | InReview | PUT | /api/indicator-item-categories/{id}
| Delete or deactivate category |  | Zain Bin Imran | 62 | High | InReview | DELETE | /api/indicator-item-categories/{id}
| Get all indicator items under a category |  | Zain Bin Imran | 63 | High | InReview | GET | /api/indicator-items/category/{categoryId}
Task 2.3.7:hospital Registration | Register a new hospital |  | Danish | 146 | High | Done | POST | /api/Hospital/AddHospital
| Update hospital’s general information |  | Danish | 147 | High | Done | PUT | /api/Hospital/UpdateHospital/{id}
| Update hospital’s approval status (Recommended, Not Recommended, Revisit) |  | Danish | 148 |  | pending | PATCH | /api/Hospital/{id}/status
| Delete or deactivate hospital record |  | Danish | 149 | High | Done | DELETE | /api/Hospital/DeleteHospital/{id}
| List hospitals by transplant type (e.g., Liver, Renal) |  | Danish | 67 | High | Inprgress | GET | /api/Hospital/transplant/{transplantTypeId}
| Get hospitals filtered by approval status (e.g., Recommended, Revisit) |  | Danish | 68 | High | Done | GET | /api/Hospital/status/{approvalStatusId}
| Fetch all hospitals that haven’t been evaluated yet |  | Danish | 69 | High | Inprgress | GET | /api/Hospital/pending
| Register a new hospital for transplant type |  |  | 70 |  | pending | POST | /api/hospitals
| Update hospital’s general information |  |  | 71 |  | pending | PUT | /api/hospitals/{id}
| Update hospital’s approval status (Recommended, Not Recommended, Revisit) |  |  | 72 |  | pending | PATCH | /api/hospitals/{id}/status
| Delete or deactivate hospital record |  |  | 73 |  | pending | DELETE | /api/hospitals/{id}
| Get complete summary (checklist, evaluation, approval) for one hospital |  |  | 74 |  | pending | GET | /api/hospitals/{id}/summary
| View AccreditationChecklist progress and marks |  |  | 75 |  | pending | GET | /api/hospitals/{id}/checklist-status
| View overall evaluation scores per standard |  |  | 76 |  | pending | GET | /api/hospitals/{id}/evaluation-status
| Upload registration or supporting documents (license, MOU, certificates) |  |  | 77 |  | pending | POST | /api/hospital-documents
| Fetch all uploaded documents for a hospital |  |  | 78 |  | pending | GET | /api/hospital-documents/{hospitalId}
| Record inspection visit details (team, date, remarks) |  |  | 79 |  | pending | POST | /api/hospital-visits
| Get visit records for a hospital |  |  | 80 |  | pending | GET | /api/hospital-visits/{hospitalId}
| Add team members (surgeon, anaesthetist, nurse, etc.) |  |  | 81 |  | pending | POST | /api/hospital-teams
| Fetch hospital’s team members |  |  | 82 |  | pending | GET | /api/hospital-teams/{hospitalId}
| Update existing team member details |  |  | 83 |  | pending | PUT | /api/hospital-teams/{id}
| Remove team member |  |  | 84 |  | pending | DELETE | /api/hospital-teams/{id}
| Save per-standard evaluation results |  |  | 85 |  | pending | POST | /api/hospital-evaluations
| Fetch all evaluation results of a hospital |  |  | 86 |  | pending | GET | /api/hospital-evaluations/{hospitalId}
| Add general evaluator remarks for a hospital |  |  | 87 |  | pending | POST | /api/hospital-remarks
| Retrieve all evaluator remarks |  |  | 88 |  | pending | GET | /api/hospital-remarks/{hospitalId}
| Generate printable summary report for one hospital |  |  | 89 |  | pending | GET | /api/hospitals/report/{hospitalId}
| Export all hospital data (Excel/CSV) |  |  | 90 |  | pending | GET | /api/hospitals/export
| Import hospital records from Excel/CSV |  |  | 91 |  | pending | POST | /api/hospitals/import
| Fetch dashboard data (total registered, approved, pending, etc.) |  |  | 92 |  | pending | GET | /api/hospitals/dashboard/summary
Task 2.3.8:hospitalStaff | Fetch all hospital team members (all hospitals) |  |  | 93 |  | pending | GET | /api/hospital-teams
| Get details of a specific team member |  |  | 94 |  | pending | GET | /api/hospital-teams/{id}
| Fetch all team members of a specific hospital |  |  | 95 |  | pending | GET | /api/hospital-teams/hospital/{hospitalId}
| Filter team members by role/designation |  |  | 96 |  | pending | GET | /api/hospital-teams/hospital/{hospitalId}?role=Surgeon
| Add new team member to a hospital |  | Usama Naseer | 97 | High | Inprgress | POST | /api/PhotaStaff/AddPhotaStaff
| Update an existing team member’s details |  | Usama Naseer | 98 | High | Inprgress | PUT | /api/PhotaStaff/UpdatePhotaStaff/{id}
| Activate/deactivate a team member |  | Usama Naseer | 99 | High | Inprgress | PATCH | /api/PhotaStaff/Activate_DeactivatePhotaStaff//{id}/status
| Remove a team member permanently |  | Usama Naseer | 100 | High | Inprgress | DELETE | /api/PhotaStaff/DeletePhotaStaff/{id}
| Bulk import team members from Excel/CSV |  |  | 101 |  | pending | POST | /api/hospital-teams/import
| Export hospital team data |  |  | 102 |  | pending | GET | /api/hospital-teams/export/{hospitalId}
| Upload license/qualification certificates (PDF, image) |  |  | 103 |  | pending | POST | /api/hospital-team-certificates
| Fetch uploaded documents of a team member |  |  | 104 |  | pending | GET | /api/hospital-team-certificates/{teamMemberId}
| Dashboard summary (total surgeons, nurses, active staff) |  |  | 105 |  | pending | GET | /api/hospital-teams/dashboard/summary
| Verify PMDC/PNC registration no. (if integrated with validation API) |  |  | 106 |  | pending | GET | /api/hospital-teams/validate-registration/{regNo}
Task 2.3.9:HospitalEvaluation | Get all hospital evaluations (with filters/pagination) |  | Zain Bin Imran | 107 |  | pending | GET | /api/hospital-evaluations | Surveyor
| Get a specific hospital evaluation record |  | Zain Bin Imran | 108 |  | pending | GET | /api/hospital-evaluations/{id} | surveyor
| Get all evaluation results for a hospital |  | Zain Bin Imran | 109 |  | pending | GET | /api/hospital-evaluations/hospital/{hospitalId} | surveyor
| Get evaluation details by standard |  | Zain Bin Imran | 110 |  | pending | GET | /api/hospital-evaluations/hospital/{hospitalId}/standard/{standardId} | surveyor
| Get total and per-standard summary |  | Zain Bin Imran | 111 |  | pending | GET | /api/hospital-evaluations/hospital/{hospitalId}/summary | surveyor
| Submit new evaluation result |  | Zain Bin Imran | 112 |  | pending | POST | /api/hospital-evaluations
| Update evaluation marks or remarks |  | Zain Bin Imran | 113 |  | pending | PUT | /api/hospital-evaluations/{id}
| Delete evaluation record |  | Zain Bin Imran | 114 |  | pending | DELETE | /api/hospital-evaluations/{id}
| Change evaluation status (Pending → Completed) |  | Zain Bin Imran | 115 |  | pending | PATCH | /api/hospital-evaluations/{id}/status
| Generate overall evaluation report for all hospitals |  | Zain Bin Imran | 116 |  | pending | GET | /api/hospital-evaluations/reports/overall
| Compare a hospital’s results against benchmarks |  | Zain Bin Imran | 117 |  | pending | GET | /api/hospital-evaluations/compare/{hospitalId}
| Export evaluation data to Excel/CSV |  | Zain Bin Imran | 118 |  | pending | GET | /api/hospital-evaluations/export
| Import evaluation records from Excel/CSV |  | Zain Bin Imran | 119 |  | pending | POST | /api/hospital-evaluations/import
| Add evaluator comment or suggestion |  | Zain Bin Imran | 120 |  | pending | POST | /api/hospital-evaluations/comments
| Retrieve evaluator comments for a hospital |  | Zain Bin Imran | 121 |  | pending | GET | /api/hospital-evaluations/comments/{hospitalId}
| Dashboard summary (average scores, top performers) |  | Zain Bin Imran | 122 |  | pending | GET | /api/hospital-evaluations/dashboard/summary
Task 2.3.10:ApprovalStatus | Fetch all available approval statuses |  |  | 123 |  | pending | GET | /api/approval-status
| Fetch details of a specific status |  |  | 124 |  | pending | GET | /api/approval-status/{id}
| Create a new approval status |  |  | 125 |  | pending | POST | /api/approval-status
| Update an existing status title/description |  |  | 126 |  | pending | PUT | /api/approval-status/{id}
| Delete or deactivate a status |  |  | 127 |  | pending | DELETE | /api/approval-status/{id}
| Get all hospitals under a specific approval status |  |  | 128 |  | pending | GET | /api/approval-status/hospitals/{statusId}
| Assign or change approval status for a hospital |  |  | 129 |  | pending | PATCH | /api/hospitals/{hospitalId}/approval-status
| Dashboard summary (count of hospitals by status) |  |  | 130 |  | pending | GET | /api/approval-status/dashboard/summary
| Fetch audit log of approval decisions (who approved & when) |  |  | 131 |  | pending | GET | /api/approval-status/audit/{hospitalId}
Task 2.3.11:PhotaStaff | Add new team member to a Phota Staff |  | Usama Naseer | 132 | High | Inprgress | POST | /api/PhotaStaff/AddPhotaStaff
| Update an existing team member’s details |  | Usama Naseer | 133 | High | Inprgress | PUT | /api/PhotaStaff/UpdatePhotaStaff/{id}
| Activate/deactivate a team member |  | Usama Naseer | 134 | High | Inprgress | PATCH | /api/PhotaStaff/Activate_DeactivatePhotaStaff//{id}/status
| Get all PhotaStaff |  | Usama Naseer | 136 | High | Inprgress | GET | /api/PhotaStaff/GetAllPhotaStaff
| Get PhotaStaff by Id |  | Usama Naseer | 137 | High | Inprgress | GET | /api/PhotaStaff/GetPhotaStaffById/{id}
| Get PhotaStaff By Email |  | Usama Naseer | 138 | High | Inprgress | GET | /api/PhotaStaff/GetPhotaStaffByEmail/{email}
Task 2.3.12:HospitalResponsibleStaff | Add new team member to a Responsible Staff |  | Zain Bin imran | 139 | High | InReview | POST | /api/PhotaStaff/AddResponsibleStaff
| Update an existing Responsible member’s details |  | Zain Bin imran | 140 | High | InReview | PUT | /api/PhotaStaff/UpdateResponsibleStaff/{id}
| Activate/deactivate a Responsible member |  | Zain Bin imran | 141 | High | InReview | PATCH | /api/PhotaStaff/Activate_DeactivateResponsibleStaff//{id}/status
| Get all Responsible Staff |  | Zain Bin imran | 143 | High | InReview | GET | /api/PhotaStaff/GetAllResponsibleStaff
| Get Responsible Staff by Id |  | Zain Bin imran | 144 | High | InReview | GET | /api/PhotaStaff/GetResponsibleStaffById/{id}
| Get Responsible Staff By Email |  | Zain Bin imran | 145 | High | InReview | GET | /api/PhotaStaff/GetResponsibleStaffByEmail/{email}
Task 2.3.14:HospitalVisits
| Add new Hospital Visit record | Creates a new hospital visit entry linked with a specific hospital and PHOTA staff member. | Zain Bin imran | 146 | High | InReview | POST | /api/HospitalVisits/AddHospitalVisit
| Update an existing Hospital Visit details | Updates hospital visit details such as visit date, remarks, or visit purpose. | Zain Bin imran | 147 | High | InReview | PUT | /api/HospitalVisits/UpdateHospitalVisit/{id}
| Approve or reject a Hospital Visit | Allows PHOTA Admin to approve or reject a hospital visit after inspection. | Zain Bin imran | 148 | High | InReview | PATCH | /api/HospitalVisits/ApproveRejectVisit/{id}/status
| Delete a Hospital Visit permanently | Deletes a specific hospital visit record permanently from the system. | Zain Bin imran | 149 | Medium | InReview | DELETE | /api/HospitalVisits/DeleteHospitalVisit/{id}
| Get all Hospital Visits | Retrieves all hospital visits with related hospital and staff details. | Zain Bin imran | 150 | High | InReview | GET | /api/HospitalVisits/GetAllHospitalVisits
| Get Hospital Visits by HospitalId | Retrieves all visits associated with a specific hospital. | Zain Bin imran | 151 | High | InReview | GET | /api/HospitalVisits/GetVisitsByHospital/{hospitalId}
| Get single Hospital Visit by Id | Fetches detailed information about a single hospital visit using its ID. | Zain Bin imran | 152 | Medium | InReview | GET | /api/HospitalVisits/GetHospitalVisitById/{id}
| Get all Pending (Unapproved) Visits | Retrieves all hospital visits that are pending approval. | Zain Bin imran | 153 | Medium | InReview | GET | /api/HospitalVisits/GetPendingHospitalVisits
| Get Visits within a date range | Returns all visits made within a given date range. | Zain Bin imran | 154 | Low | InReview | GET | /api/HospitalVisits/GetVisitsByDateRange?fromDate=yyyy-MM-dd&toDate=yyyy-MM-dd
| Get Renewal-Related Visits | Retrieves all hospital visits conducted for renewal purposes after subscription expiry. | Zain Bin imran | 155 | Medium | InReview | GET | /api/HospitalVisits/GetRenewalVisits
| Flag Visit on Expired Subscription | Marks a visit as a renewal visit when the hospital’s subscription has expired. | Zain Bin imran | 156 | High | InReview | PATCH | /api/HospitalVisits/FlagAsRenewalVisit/{visitId}
Task 2.3.15:PhotaDepartment | Add new department |  | Usama | 319 | High | InReview | POST | /api/PhotaDepartment/AddDepartment
| Update an existing department |  | Usama | 320 | High | InReview | PUT | /api/PhotaDepartment/UpdateDepartment/{id}
| Activate/deactivate a department |  | Usama | 321 | High | InReview | PATCH | /api/PhotaDepartment/Activate_DeactivateDepartment/{id}/status
| Get all departments |  | Usama | 322 | High | InReview | GET | /api/PhotaDepartment/GetAllDepartments
| Get department by Id |  | Usama | 323 | High | InReview | GET | /api/PhotaDepartment/GetDepartmentById/{id}
| Get department by name |  | Usama | 324 | High | InReview | GET | /api/PhotaDepartment/GetDepartmentByName/{name}
Task 2.3.16:PhotaDesignation
| Add new designation |  | Usama | 325 | High | InReview | POST | /api/PhotaDesignation/AddDesignation
| Update an existing designation |  | Usama | 326 | High | InReview | PUT | /api/PhotaDesignation/UpdateDesignation/{id}
| Activate/deactivate a designation |  | Usama | 327 | High | InReview | PATCH | /api/PhotaDesignation/Activate_DeactivateDesignation/{id}/status
| Get all designations |  | Usama | 328 | High | InReview | GET | /api/PhotaDesignation/GetAllDesignations
| Get designation by Id |  | Usama | 329 | High | InReview | GET | /api/PhotaDesignation/GetDesignationById/{id}
| Get designation by name |  | Usama | 330 | High | InReview | GET | /api/PhotaDesignation/GetDesignationByName/{name}
Task 2.3.17:PhotaEmploymentType
| Add new employment type |  | Usama | 331 | High | InReview | POST | /api/PhotaEmploymentType/AddEmploymentType
| Update an existing employment type |  | Usama | 332 | High | InReview | PUT | /api/PhotaEmploymentType/UpdateEmploymentType/{id}
| Activate/deactivate an employment type |  | Usama | 333 | High | InReview | PATCH | /api/PhotaEmploymentType/Activate_DeactivateEmploymentType/{id}/status
| Get all employment types |  | Usama | 334 | High | InReview | GET | /api/PhotaEmploymentType/GetAllEmploymentTypes
| Get employment type by Id |  | Usama | 335 | High | InReview | GET | /api/PhotaEmploymentType/GetEmploymentTypeById/{id}
| Get employment type by name |  | Usama | 336 | High | InReview | GET | /api/PhotaEmploymentType/GetEmploymentTypeByName/{name}
Task 2.3.18:UserType
| Add new user type |  | Usama | 337 | High | InReview | POST | /api/UserType/AddUserType
| Update an existing user type |  | Usama | 338 | High | InReview | PUT | /api/UserType/UpdateUserType/{id}
| Activate/deactivate a user type |  | Usama | 339 | High | InReview | PATCH | /api/UserType/Activate_DeactivateUserType/{id}/status
| Get all user types |  | Usama | 340 | High | InReview | GET | /api/UserType/GetAllUserTypes
| Get user type by Id |  | Usama | 341 | High | InReview | GET | /api/UserType/GetUserTypeById/{id}
| Get user type by name |  | Usama | 342 | High | InReview | GET | /api/UserType/GetUserTypeByName/{name}
Task 2.4: Hospital Subscription
Task 2.4.1:HospitalSubscriptions
|  | Creates a new hospital subscription linked with a hospital, transplant type, and related hospital visit. Includes subscription start & end dates and total fee. | Zain Bin Imran | 157 | High | pending | POST | /api/HospitalSubscriptions/AddHospitalSubscription
| Update existing Hospital Subscription details | Updates fields such as transplant type, fee amount, or subscription duration. | Zain Bin Imran | 158 | High | pending | PUT | /api/HospitalSubscriptions/UpdateHospitalSubscription/{id}
| Mark Subscription as Fully Paid | Updates the IsFullyPaid flag to true once all payments have been completed. | Zain Bin Imran | 159 | High | pending | PATCH | /api/HospitalSubscriptions/MarkAsFullyPaid/{id}
| Activate or Deactivate Subscription | Toggles the IsActive flag to activate or deactivate a hospital’s subscription record. | Zain Bin Imran | 160 | High | pending | PATCH | /api/HospitalSubscriptions/ActivateDeactivateSubscription/{id}/status
| Renew Hospital Subscription | Creates a new record when an existing subscription expires; automatically deactivates the previous one. | Zain Bin Imran | 161 | High | pending | POST | /api/HospitalSubscriptions/RenewSubscription/{hospitalId}
| Delete Hospital Subscription | Permanently removes a subscription record (only if inactive or test entry). | Zain Bin Imran | 162 | Medium | pending | DELETE | /api/HospitalSubscriptions/DeleteHospitalSubscription/{id}
| Get all Hospital Subscriptions | Retrieves all hospital subscriptions with hospital, transplant type, and related visit info. | Zain Bin Imran | 163 | High | pending | GET | /api/HospitalSubscriptions/GetAllHospitalSubscriptions
| Get Subscription by Id | Returns a single subscription’s complete details using its ID. | Zain Bin Imran | 164 | Medium | pending | GET | /api/HospitalSubscriptions/GetSubscriptionById/{id}
| Get Active Subscriptions | Fetches all subscriptions where IsActive = 1. | Zain Bin Imran | 165 | High | pending | GET | /api/HospitalSubscriptions/GetActiveSubscriptions
| Get Expired Subscriptions | Lists subscriptions where SubscriptionEndDate < current date. | Zain Bin Imran | 166 | Medium | pending | GET | /api/HospitalSubscriptions/GetExpiredSubscriptions
| Get Subscriptions by Hospital | Fetches all subscriptions associated with a specific hospital. | Zain Bin Imran | 167 | High | pending | GET | /api/HospitalSubscriptions/GetSubscriptionsByHospital/{hospitalId}
| Get Subscriptions by Transplant Type | Filters subscriptions based on transplant type (Renal, Liver, Corneal, Bone Marrow, etc.). | Zain Bin Imran | 168 | Medium | pending | GET | /api/HospitalSubscriptions/GetSubscriptionsByTransplantType/{transplantTypeId}
| Link Subscription with Hospital Visit | Links an existing Hospital Visit record to a subscription for tracking approval or inspection visits. | Zain Bin Imran | 169 | Medium | pending | PATCH | /api/HospitalSubscriptions/LinkHospitalVisit/{subscriptionId}/{visitId}
Task 2.4.2:HospitalPayments
| Creates a new payment entry for a specific hospital subscription (includes total, paid, and remaining amounts). | Creates a new payment entry for a specific hospital subscription (includes total, paid, and remaining amounts). | Zain Bin Imran | 170 | High | pending | POST | /api/Payments/AddPayment
| Update existing Payment details | Updates payment details such as paid amount, remaining amount, or payment status. | Danish Rajpoot | 171 | High | pending | PUT | /api/Payments/UpdatePayment/{id}
| Add installment payment | Adds an installment to the existing subscription payment and recalculates remaining amount. | Danish Rajpoot | 172 | High | pending | PATCH | /api/Payments/AddInstallment/{id}
| Update Payment Status | Updates the PaymentStatus field (e.g., from Partially Paid to Paid). | Danish Rajpoot | 173 | High | pending | PATCH | /api/Payments/UpdatePaymentStatus/{id}
| Delete Payment record | Deletes a payment entry (usually used for test or incorrect data). | Danish Rajpoot | 174 | Medium | pending | DELETE | /api/Payments/DeletePayment/{id}
| Get all Payments | Retrieves all payments including hospital, subscription, and payment status details. | Danish Rajpoot | 175 | High | pending | GET | /api/Payments/GetAllPayments
| Get Payment by Id | Returns detailed information of a specific payment record by ID. | Danish Rajpoot | 176 | Medium | pending | GET | /api/Payments/GetPaymentById/{id}
| Get Payments by SubscriptionId | Lists all payments made for a particular hospital subscription. | Danish Rajpoot | 177 | High | pending | GET | /api/Payments/GetPaymentsBySubscription/{subscriptionId}
| Get Pending Payments | Retrieves all payment records where status is Pending or Partially Paid. | Danish Rajpoot | 178 | Medium | pending | GET | /api/Payments/GetPendingPayments
| Get Fully Paid Subscriptions | Returns all payments where status is Paid (fully cleared). | Danish Rajpoot | 179 | Medium | pending | GET | ssssssssssssss
Task 2.4.3:PaymentInstallments | [7 empty] | Endpoint
| Add new Payment Installment | Adds a new installment entry against a specific Payment. | Zain Bin Imran | 180 | High | pending | POST | /api/PaymentInstallments/AddInstallment
| Update Payment Installment | Updates installment details like amount, date, or method. | Zain Bin Imran | 181 | Medium | pending | PUT | /api/PaymentInstallments/UpdateInstallment/{id}
| Delete Payment Installment | Deletes an installment record (for corrections or admin operations). | Zain Bin Imran | 182 | Medium | pending | DELETE | /api/PaymentInstallments/DeleteInstallment/{id}
| Get all Payment Installments | Retrieves all installment records (can be filtered by Payment or Hospital). | Zain Bin Imran | 183 | High | pending | GET | /api/PaymentInstallments/GetAllInstallments
| Get Installment by Id | Returns details of a specific installment record. | Zain Bin Imran | 184 | Medium | pending | GET | /api/PaymentInstallments/GetInstallmentById/{id}
| Get Installments by PaymentId | Fetches all installments linked to a particular Payment record. | Zain Bin Imran | 185 | High | pending | GET | /api/PaymentInstallments/GetInstallmentsByPayment/{paymentId}
| Get Total Paid Amount for Payment | Calculates and returns total amount paid in installments for a Payment. | Zain Bin Imran | 186 | High | pending | GET | /api/PaymentInstallments/GetTotalPaidByPayment/{paymentId}
Task 2.4.4:SubscriptionHistory | Add new Subscription History | Add a new history record when subscription changes (e.g., Active → Expired). | Danish Rajpoot | 187 | High | pending | POST | /api/SubscriptionHistory/AddHistory
| Update Subscription History | Update an existing history record (for correction). | Danish Rajpoot | 188 | Medium | pending | PUT | /api/SubscriptionHistory/UpdateHistory/{id}
| Delete Subscription History | Permanently remove a specific history record (admin-only). | Danish Rajpoot | 189 | Low | pending | DELETE | /api/SubscriptionHistory/DeleteHistory/{id}
| Get all Subscription Histories | Retrieve all subscription history records. | Danish Rajpoot | 190 | Medium | pending | GET | /api/SubscriptionHistory/GetAllHistories
| Get Subscription History by Id | Get a specific history record by its Id. | Danish Rajpoot | 191 | Medium | pending | GET | /api/SubscriptionHistory/GetHistoryById/{id}
| Get Current History by Subscription | Fetch latest (current) history record of a specific subscription. | Danish Rajpoot | 192 | High | pending | GET | /api/SubscriptionHistory/GetCurrentHistoryBySubscription/{subscriptionId}
| Get History Records by Subscription | Retrieve full status change history for a subscription. | Danish Rajpoot | 193 | High | pending | GET | /api/SubscriptionHistory/GetHistoryBySubscription/{subscriptionId}
Task 2.5: Staff And Users
Task 2.5.1:HospitalVisitTeam
| Get All Hospital Visit Team | Retrieve all hospital visit team records | Zain | 194 | High | Active | GET | /api/hospitalvisitteam/getall
| Get Hospital Visit Team By ID | Retrieve a single hospital visit team record by ID | Zain | 195 | High | Active | GET | /api/hospitalvisitteam/getbyid/{id}
| Create Hospital Visit Team | Add a new hospital visit team record | Zain | 196 | High | Active | POST | /api/hospitalvisitteam/create
| Update Hospital Visit Team | Update existing hospital visit team record by ID | Zain | 197 | Medium | Active | PUT | /api/hospitalvisitteam/update/{id}
| SoftDelete Hospital Visit Team | Delete a hospital visit team record by ID | Zain | 198 | Medium | Active | DELETE | /api/hospitalvisitteam/delete/{id}
Task 2.5.2:PhotaStaff
| Get All Phota Staff | Retrieve all staff records |  | 199 | High | Active | GET | /api/phota_staff/getall
| Get Phota Staff By ID | Retrieve single staff record by ID |  | 200 | High | Active | GET | /api/phota_staff/getbyid/{id}
| Create Phota Staff | Add a new staff record |  | 201 | High | Active | POST | /api/phota_staff/create
| Update Phota Staff | Update existing staff record by ID |  | 202 | Medium | Active | PUT | /api/phota_staff/update/{id}
| SoftDelete Phota Staff | SoftDelete staff record by ID |  | 203 | Medium | Active | DELETE | /api/phota_staff/delete/{id}
| Search Phota Staff | Search staff by name, CNIC, or designation |  | 204 | Medium | Active | GET | /api/phota_staff/search?keyword={text}
| Get Staff By Designation | Retrieve all staff with specific designation |  | 205 | Low | Active | GET | /api/phota_staff/getbydesignation/{designation}
| Get Staff By User ID | Retrieve staff info linked to a specific user |  | 206 | Medium | Active | GET | /api/phota_staff/getbyuserid/{user_id}
Task 2.5.3:HospitalStaffProfile | Get All Hospital Staff Profiles | Retrieve all hospital staff profile records |  | 207 | High | Active | GET | /api/hospital_staff_profile/getall
| Get Hospital Staff Profile By ID | Retrieve a single hospital staff profile by ID |  | 208 | High | Active | GET | /api/hospital_staff_profile/getbyid/{id}
| Create Hospital Staff Profile | Add a new hospital staff profile record |  | 209 | High | Active | POST | /api/hospital_staff_profile/create
| Update Hospital Staff Profile | Update existing hospital staff profile record by ID |  | 210 | Medium | Active | PUT | /api/hospital_staff_profile/update/{id}
| Delete Hospital Staff Profile | Delete a hospital staff profile record by ID |  | 211 | Medium | Active | DELETE | /api/hospital_staff_profile/delete/{id}
| Get Staff Profiles By Hospital ID | Retrieve all staff profiles for a specific hospital |  | 212 | Medium | Active | GET | /api/hospital_staff_profile/getbyhospital/{hospital_id}
| Get Staff Profiles By Indicator ID | Retrieve all staff profiles for a specific indicator |  | 213 | Medium | Active | GET | /api/hospital_staff_profile/getbyindicator/{indicator_id}
| Get Staff Profile By User ID | Retrieve staff profile linked to a specific user |  | 214 | Low | Active | GET | /api/hospital_staff_profile/getbyuserid/{user_id}

## Hospital_registration_Frontend
http://10.10.35.190:2400/
| Task_Id | Interface_Title | Deadline | Resourse | Status | Pull Request | Reviewed_By | Reviewed_Remarks | Review Date
Authentication | 1 | Login page | 2025-11-13 | Maaz | InReview | please pull | Aqsa
| 2 | Forget Password | 2025-11-13 | Maaz | InReview | please pull | Aqsa
| 3 | OTP Generation | 2025-11-13 | Maaz | InReview | please pull | Aqsa
| 4 | Confirmation | 2025-11-13 | Maaz | InReview | please pull | Aqsa
| 5 | Users Management | 2025-11-13 | Aqsa | InReview | please pull | Moaz
Configuration | 6 | Sops Management | 2025-11-13 | Maaz | InReview | please pull | Aqsa | All is ok review complete | 13-11-25
| 7 | Dashboard and Menues | 2025-11-14 | Moaz
| 8 | Roles and Permissions | 2025-11-14 | Aqsa
| 9 | Phota Staff Profiles Management | 2025-11-14 | Aqsa
| 10 | Departments and Designations Managements | 2025-11-14 | Aqsa
Hospital Registration | 11 | Hospital Configuration | 2025-11-14 | Aqsa
| 12 | Tentative Visit Plan
| 13 | Fee Payment
| 14 | Final Visit Plan
| 15 | Hospital Survey and Assessment
| 16 | Hospital Staff Profiles and Assessment
| 17 | Marks and Evaluation
| 18 | Accredetation Report
| 19 | Renewal
Case Managment | 20 | Case Approval and Payment
| 21 | Case History
| 22 | Donars and Recepient Details
| 23 | History of Patients
| 24 | Reports

## Case Management
Gantt Chart Outline
Phase | Task Name | Start Date | End Date | Duration
Project Planning & Design | Requirement Gathering | 2024-01-01 | 2024-03-01 | 3 days
| Project Scope Definition | 2024-04-01 | 2024-06-01 | 3 days
| Website Design and Layout | 2024-07-01 | 14/01/2024 | 7 days
| Database Schema Design | 15/01/2024 | 17/01/2024 | 3 days
| Tech Stack Finalization | 18/01/2024 | 20/01/2024 | 3 days
Backend Development | Backend Setup | 21/01/2024 | 25/01/2024 | 5 days
| Authentication & Authorization | 26/01/2024 | 28/01/2024 | 3 days
| Admin Management | 29/01/2024 | 15/02/2024 | 18 days
| Payment Gateway Integration | 16/02/2024 | 18/02/2024 | 3 days
| Booking & Scheduling Management | 19/02/2024 | 22/02/2024 | 4 days
| API Testing and Debugging | 23/02/2024 | 25/02/2024 | 3 days
Frontend Development | Frontend Setup (React) | 26/02/2024 | 28/02/2024 | 3 days
| Ride Booking System | 2024-01-03 | 15/03/2024 | 15 days
| Vehicle and Driver Selection | 16/03/2024 | 18/03/2024 | 3 days
| Payment & Fare Options | 19/03/2024 | 21/03/2024 | 3 days
| Ride Tracking & Notifications | 22/03/2024 | 25/03/2024 | 4 days
Integration & Features | Geo-Tracking & Maps Integration | 26/03/2024 | 28/03/2024 | 3 days
| Notification System Integration | 29/03/2024 | 31/03/2024 | 3 days
Security & Compliance | Security Protocols Implementation | 2024-01-04 | 2024-03-04 | 3 days
| Document Verification System | 2024-04-04 | 2024-06-04 | 3 days
Testing & Deployment | Unit Testing & Bug Fixing | 2024-07-04 | 2024-10-04 | 4 days
| UAT Testing | 2024-11-04 | 13/04/2024 | 3 days
| Go-Live Deployment | 14/04/2024 | 15/04/2024 | 2 days
Post-Launch & Maintenance | Regular Monitoring & Bug Fixes | 16/04/2024 | Ongoing | Ongoing

## Sheet2
ALL Layers Should Be Seperate
Sr # | Layer | Description | Status
1 | travelaride.core | 2 folders 1. Entities (All models + every type of entity) a) Must be a base entity which has i) InsertedId ii) InsertedDate iii) UpdatedId iv) UpdatedDate public class BaseEntity { public bool IsActive { get; set; } = true; public DateTime InsertedDate { get; set; } = DateTime.Now; [StringLength(50)] public string? InsertedId { get; set; } public DateTime? UpdatedDate { get; set; } = DateTime.Now; [StringLength(50)] public string? UpdatedId { get; set; } } b) Authentication Folder (all entities related to authentication) 2. Enums public enum TARRoles { Admin, Sale, Account, Passenger, Driver } public enum Twofactortypes { email, sms, authenticator } | Not Implemented
2 | travelaride.Data | 2 folders 1. Models a) ApplicationDBContext.cs b) DbConnector.cs public class DbConnector { private readonly IConfiguration _configuration; protected DbConnector(IConfiguration configuration) { _configuration = configuration; } public IDbConnection CreateConnection() { string connectionString = _configuration.GetConnectionString("DefaultConnection"); return new SqlConnection(connectionString); } } 2. Migrations | Not Implemented
3 | travelaride.Services | No Folder Just 2 things 1) Interface 2) Service 1. IEmailService 2. EmailService (All email related functions here) 3. IUserManagementService 4. UserManagementService (all user related functions here) | Not Implemented
NOTE: | Please Don't use int/double for IDs in database Use GUID for all types of IDs | public int Id { get; set; } Wrong [Key] [StringLength(50)] public string Id { get; set; } Right